## Project Charter
## Project Purpose
The current workforce management (WFM) software used by the customer service (CS) department was built for a team of 50–100 agents. The CS team has since grown to 150–200 agents, which has led to serious system performance issues. Lag in the software has caused agents to stop checking schedules regularly, increasing the risk of missed shifts and scheduling conflicts. Short-notice changes are avoided by WFM due to poor visibility and agent disengagement.
Absences are currently 100% manually approved by WFM against defined capacity thresholds. The goal is to approve 75% of absences automatically with the new tool, saving WFM up to **8 hours of manual work per week**. Legal exceptions will still require manual review.
There are no real-time monitoring dashboards in place. The new system will enable queue-level tracking (phone, chat, email), allowing the organization to hire a **real-time monitor**, with the goal of improving SLA performance to **95%**.
Manual processing for channel assignments will be replaced by automated scheduling logic, again saving WFM up to **8 hours per week**. The software introduces clearer access controls to reduce scheduling errors by team leads and managers.
Although forecasting will continue to be done externally, the new tool will assess forecast accuracy and output performance metrics to support improved future forecasting.
The new software is compliant with company security policies and will use two-factor authentication, ensuring **GDPR-compliant access** and protection of personal data.
---
## Key Stakeholders
- **Project Lead:** Lotti (responsible for planning, execution, and stakeholder alignment)
- **Vendor:** Provides platform, training for admins, daily support, and weekly check-ins
- **WFM Team:** Supports setup, configuration, and process design
- **IT & Security:** Ensures system compatibility, performs security reviews and whitelisting
- **Data Team:** Integrates WFM data into the data warehouse and ensures analytics continuity
- **CS Management & Leadership:** Receives regular updates and communicates rollout details to team leads, coaches, and agents
- **End Users:** All customer service employees, including agents, seniors, leads, coaches, and managers, will be trained and onboarded to the new system
---
## Scope
**Included:**
- System configuration and integration
- Training for all CS employees
- Automation of absence approval and scheduling
- Rollout in multiple stages (by teams)
- Embedding of data connectors into the data warehouse
- Post-rollout monitoring, KPIs tracking, and improvements
- Creation of dashboards, training material, and documentation
**Out of Scope:**
- Forecasting logic (still handled externally)
- Custom integrations not provided by vendor out-of-the-box
- Changes to contractual scheduling frameworks or work agreements
---
## Constraints & Assumptions
- **Phone shifts will change** from 2 daily blocks to 1–3 flexible blocks, improving scheduling flexibility but requiring adjustment by agents.
- **Absence policy enforcement** will become stricter; fewer manual exceptions will be allowed.
- A **temporary productivity dip (~10%)** is expected during the first two weeks post-rollout due to change adaptation.
- Coaches and managers will lose some direct scheduling access, requiring stricter process adherence and reminders to use official WFM channels.
- The rollout will be planned during a **low contact volume period** to minimize impact.
- Some integration testing and validation will rely on availability of external systems (CRM, telephony, etc.).
---
## Success Metrics
¦ Goal ¦ Target ¦
¦------¦--------¦
¦ Schedule accuracy improvement ¦ +15% ¦
¦ SLA performance (chat, phone, email) ¦ 95% ¦
¦ Absences auto-approved ¦ 75% ¦
¦ WFM manual effort reduction ¦ -8 hours/week ¦
¦ Scheduling errors caused by unauthorized edits ¦ 0 ¦
¦ Forecast accuracy tracking ¦ Enabled and reviewed monthly ¦
¦ Productivity impact post-rollout ¦ Recovery to baseline within 2 weeks ¦
¦ Agent engagement with schedules (views per week) ¦ +30% from baseline ¦
---

## Break-Down
Task | Owner(s) | Comments
1. Project Initiation & Planning
Define project goals and success metrics (e.g. improve schedule accuracy by X%, reduce manual work by Y%) | Lead & WFM
Define project timeline and milestones | Lead & WFM
Assign project roles and responsibilities | Lead
Conduct stakeholder alignment meetings (CS leadership, IT/Security, Data) | Lead
2. Access, Security & IT Setup
Perform access control and permissions setup (agents, leads, WFM) | Lead
Security and compliance review (privacy, data handling) | IT
IT sign-off on software compatibility / whitelisting | IT
3. Testing & Validation
User Acceptance Testing (UAT) with subset of users | Lead
Integration testing (connectors to ticketing, CRM, telephony) | Lead
Backup and rollback plan testing | Lead
Monitoring tools setup (uptime tracking, error logging) | Lead
4. System Setup & Configuration
Clean and validate legacy data before import
Data import & initial system setup | Lead & WFM
Integration of data connectors to data warehouse | Lead & Data
Design data dictionary for future export/reporting | Lead & Data
Import absence data from old software | Lead
Queue/channel-level configuration (chat vs. email vs. phone) | Lead & Data
Skill & proficiency tagging (for skill-based routing) | Lead
5. Experimentation & Process Design
Experimentation: Forecasting & scheduling | Lead & WFM
Experimentation: Holiday planning & processes | Lead & WFM
Define & document forecasting/scheduling processes | Lead & WFM
Define & document holiday planning processes | Lead & WFM
Set up automation rules (e.g., breaks, adherence alerts) | Lead
Set up wfm dashboard | Lead
6. Training & Communication
Create training materials for CS employees | Lead
Train CS employees | Lead
Inform all stakeholders of roll-out date (IT, CS, Data, C-level) | Lead
Create knowledge base for CS employees | Lead
Create knowledge base for WFM employees | Lead
Create Slack channels for real-time support during rollout | Lead
7. Transition & Scheduling
Create schedules for upcoming 4 weeks in both old & new systems | WFM
Create backup schedules for emergencies | WFM
connect existing dashboards to new data source | Lead
8. Post-Rollout & Monitoring
First-week hypercare support (questions, fixes) | WFM
Weekly stakeholder check-ins (first 4 weeks) | Lead
Post-implementation review (what went well, areas for improvement) | Lead
Track KPIs post-rollout (compare pre-/post- rollout metrics) | WFM
Plan for future features or integrations | Lead & WFM

## Timelines
Tasks
Week | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16
Weekday | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
1. Project Initiation & Planning | a | a | a | a
Define project goals and success metrics |  | b
Define project timeline and milestones |  | b
Assign project roles and responsibilities |  | b
Plan stakeholder alignment meetings (CS leadership, IT/Security, Data) |  |  | b
2. Access, Security & IT Setup |  |  |  |  | a | a | a | a
Perform access control and permissions setup (agents, leads, WFM) |  |  |  |  | b | b
Security and compliance review (privacy, data handling) |  |  |  |  | b | b | b
IT sign-off on software compatibility / whitelisting | [7 empty] | b
4. System Setup & Configuration | [8 empty] | a | a | a | a | a | a | a | a | a | a | a | a
Clean and validate legacy data before import | [8 empty] | b | b | b
Data import & initial system setup | [11 empty] | b | b | b
Integration of data connectors to data warehouse | [12 empty] | b | b | b
Design data dictionary for future export/reporting | [12 empty] | b | b | b
Import absence data from old software | [15 empty] | b | b | b
Queue/channel-level configuration (chat vs. email vs. phone) | [15 empty] | b | b | b
Skill & proficiency tagging (for skill-based routing) | [18 empty] | b | b
3. Testing & Validation | [15 empty] | a | a | a | a | a
User Acceptance Testing (UAT) with subset of users | [17 empty] | b | b
Integration testing (connectors to ticketing, CRM, telephony) | [15 empty] | b | b
Backup and rollback plan testing | [15 empty] | b | b
Monitoring tools setup (uptime tracking, error logging) | [17 empty] | b | b | b
5. Experimentation & Process Design | [20 empty] | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
Experimentation: Forecasting & scheduling | [20 empty] | b | b | b | b | b | b | b | b | b | b | b | b
Experimentation: Holiday planning & processes | [25 empty] | b | b | b | b | b | b | b | b | b | b | b | b
Define & document forecasting/scheduling processes | [30 empty] | b | b | b | b | b | b | b | b | b | b
Define & document holiday planning processes | [35 empty] | b | b | b | b | b
Set up automation rules (e.g., breaks, adherence alerts) | [25 empty] | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
Set up wfm dashboard | [35 empty] | b | b | b | b | b | b | b | b | b | b
6. Training & Communication | [40 empty] | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
Create training materials for CS employees | [40 empty] | b | b | b | b | b
Train CS employees | [47 empty] | b | b | [8 empty] | b | b | [8 empty] | b | b
Inform all stakeholders of roll-out date (IT, CS, Data, C-level) | [43 empty] | b
Create knowledge base for CS employees | [42 empty] | b | b | b | b | b | b | b | b | b | b
Create knowledge base for WFM employees | [42 empty] | b | b | b | b | b | b | b | b | b | b | b | b | b
Create Slack channels for real-time support during rollout | [50 empty] | b
7. Transition & Scheduling Team 1 | [51 empty] | a | a | a | a | a | a | a
Create schedules for upcoming 4 weeks in both old & new systems | [51 empty] | b | b | b
Create backup schedules for emergencies | [54 empty] | b | b
connect existing dashboards to new data source | [57 empty] | b
Go-Live Team 1 | [57 empty] | b
7. Transition & Scheduling Teams 2-5 | [58 empty] | a | a | a | a | a | a | a | a | a | a
Create schedules for upcoming 4 weeks in both old & new systems | [58 empty] | b | b | b | b | b
Create backup schedules for emergencies | [63 empty] | b | b | b
connect existing dashboards to new data source | [67 empty] | b
Go-Live Teams 2-5 | [67 empty] | b
7. Transition & Scheduling Teams 6-8 | [65 empty] | a | a | a | a | a | a | a | a
Create schedules for upcoming 4 weeks in both old & new systems | [65 empty] | b | b | b | b
Create backup schedules for emergencies | [69 empty] | b | b | b
connect existing dashboards to new data source | [72 empty] | b
Go-Live Teams 6-8 | [72 empty] | b
8. Post-Rollout & Monitoring | [55 empty] | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
Archive old processes, request forms, knowledge base articles | [73 empty] | b
First-week hypercare support (questions, fixes) | [57 empty] | b | b | b | b | b | b |  |  |  |  | b | b | b | b | b | b | b | b | b | b | b
Weekly stakeholder check-ins (first 4 weeks) | [61 empty] | b |  |  |  |  | b |  |  |  |  | b |  |  |  |  | b
Post-implementation review (what went well, areas for improvement) | [78 empty] | b
Track KPIs post-rollout (compare pre-/post- rollout metrics) | [75 empty] | b | b | b | b | b
Plan for future features or integrations