## Timelines
Tasks
Week | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16
Weekday | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
1. Project Initiation & Planning | a | a | a | a
Define project goals and success metrics |  | b
Define project timeline and milestones |  | b
Assign project roles and responsibilities |  | b
Plan stakeholder alignment meetings (CS leadership, IT/Security, Data) |  |  | b
2. Access, Security & IT Setup |  |  |  |  | a | a | a | a
Perform access control and permissions setup (agents, leads, WFM) |  |  |  |  | b | b
Security and compliance review (privacy, data handling) |  |  |  |  | b | b | b
IT sign-off on software compatibility / whitelisting | [7 empty] | b
4. System Setup & Configuration | [8 empty] | a | a | a | a | a | a | a | a | a | a | a | a
Clean and validate legacy data before import | [8 empty] | b | b | b
Data import & initial system setup | [11 empty] | b | b | b
Integration of data connectors to data warehouse | [12 empty] | b | b | b
Design data dictionary for future export/reporting | [12 empty] | b | b | b
Import absence data from old software | [15 empty] | b | b | b
Queue/channel-level configuration (chat vs. email vs. phone) | [15 empty] | b | b | b
Skill & proficiency tagging (for skill-based routing) | [18 empty] | b | b
3. Testing & Validation | [15 empty] | a | a | a | a | a
User Acceptance Testing (UAT) with subset of users | [17 empty] | b | b
Integration testing (connectors to ticketing, CRM, telephony) | [15 empty] | b | b
Backup and rollback plan testing | [15 empty] | b | b
Monitoring tools setup (uptime tracking, error logging) | [17 empty] | b | b | b
5. Experimentation & Process Design | [20 empty] | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
Experimentation: Forecasting & scheduling | [20 empty] | b | b | b | b | b | b | b | b | b | b | b | b
Experimentation: Holiday planning & processes | [25 empty] | b | b | b | b | b | b | b | b | b | b | b | b
Define & document forecasting/scheduling processes | [30 empty] | b | b | b | b | b | b | b | b | b | b
Define & document holiday planning processes | [35 empty] | b | b | b | b | b
Set up automation rules (e.g., breaks, adherence alerts) | [25 empty] | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
Set up wfm dashboard | [35 empty] | b | b | b | b | b | b | b | b | b | b
6. Training & Communication | [40 empty] | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
Create training materials for CS employees | [40 empty] | b | b | b | b | b
Train CS employees | [47 empty] | b | b | [8 empty] | b | b | [8 empty] | b | b
Inform all stakeholders of roll-out date (IT, CS, Data, C-level) | [43 empty] | b
Create knowledge base for CS employees | [42 empty] | b | b | b | b | b | b | b | b | b | b
Create knowledge base for WFM employees | [42 empty] | b | b | b | b | b | b | b | b | b | b | b | b | b
Create Slack channels for real-time support during rollout | [50 empty] | b
7. Transition & Scheduling Team 1 | [51 empty] | a | a | a | a | a | a | a
Create schedules for upcoming 4 weeks in both old & new systems | [51 empty] | b | b | b
Create backup schedules for emergencies | [54 empty] | b | b
connect existing dashboards to new data source | [57 empty] | b
Go-Live Team 1 | [57 empty] | b
7. Transition & Scheduling Teams 2-5 | [58 empty] | a | a | a | a | a | a | a | a | a | a
Create schedules for upcoming 4 weeks in both old & new systems | [58 empty] | b | b | b | b | b
Create backup schedules for emergencies | [63 empty] | b | b | b
connect existing dashboards to new data source | [67 empty] | b
Go-Live Teams 2-5 | [67 empty] | b
7. Transition & Scheduling Teams 6-8 | [65 empty] | a | a | a | a | a | a | a | a
Create schedules for upcoming 4 weeks in both old & new systems | [65 empty] | b | b | b | b
Create backup schedules for emergencies | [69 empty] | b | b | b
connect existing dashboards to new data source | [72 empty] | b
Go-Live Teams 6-8 | [72 empty] | b
8. Post-Rollout & Monitoring | [55 empty] | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
Archive old processes, request forms, knowledge base articles | [73 empty] | b
First-week hypercare support (questions, fixes) | [57 empty] | b | b | b | b | b | b |  |  |  |  | b | b | b | b | b | b | b | b | b | b | b
Weekly stakeholder check-ins (first 4 weeks) | [61 empty] | b |  |  |  |  | b |  |  |  |  | b |  |  |  |  | b
Post-implementation review (what went well, areas for improvement) | [78 empty] | b
Track KPIs post-rollout (compare pre-/post- rollout metrics) | [75 empty] | b | b | b | b | b
Plan for future features or integrations